## Change Tracker
Sr No | Phase | Module | Description | Status | Remark
1 | P1 | Global | Rebrand: Influere→iCollaborate, remove 'Work Order' wording from user panel, new logo, new favicon | Done | Rebrand+logo+favicon done (P1). Remaining user-facing 'Work Order' wording removed from consultancy & collaboration pages (P2/P4): consultancy->Request, collaboration->Campaign/brief. Code identifiers (work-order-*, workOrder*) left intact per Decision #3.
2 | P6 | Front-End / Home | Hexagon honeycomb (8 around bold centre, flip to rectangles on scroll); replace intro content; add heading 'What is iCollaborate.ai' | Done | Hexagon honeycomb rebuilt with SCROLL-SCRUBBED flip (per user choice): tight flat-top beehive (8 hexes around bold central hex). Scroll progress (0-1) drives both un-packing (--spread var: cols overlap -> gapped grid) and a staggered rotateY flip of the 8 surround hexes into rectangular cards; reverses on scroll up. Solves first-fold issue (no load-time auto-flip). Center hex bold (gradient wordmark, purple ring). Mobile: static cards. Content+heading handled separately.
3 | P6 | Front-End / All pages | Add onload / on-scroll animations & transitions | Done | Added reusable useScrollReveal hook (IntersectionObserver) + [data-animate]/.is-visible CSS in index.css with prefers-reduced-motion fallback. Applied to Home sections (hero onload + about/why-join/professional/info on-scroll) and Registration content (per-step).
4 | P2 | User Panel / Consultancy (Legal) | Remove work-order form; add new descriptive copy under Legal headline | Done | Legal: removed work-order form; added per-category description under headline (Legal = exact client copy), smaller font. AI badge work-order wording removed.
5 | P2 | User Panel / Consultancy (Legal) | Filters: remove Availability; new Type of Service; Rate dual-bar ($10-$100K); Distance (City/Provincial/National/International); Experience dual-bar (0-50 yrs) | Done | Filters rebuilt: removed Availability; Type of Service per-category (legal list per spec); Rate dual-bar $10-$100K; Distance City/Provincial/National/International; Experience dual-bar 0-50 yrs.
6 | P2 | User Panel / Consultancy detail | Professional page: replace URL-title with description; remove Tax Filing box; rebuild Book Appointment form (Description¦Attachments¦Schedule call optional); add support icon + popup (Name/Email/Message) | Done | Professional page: summary->CA description; removed service boxes; rebuilt Book an Appointment form (Description¦Attachments¦Schedule voice/video call optional); added support headset icon by name -> SupportContactModal (Name/Email/Message).
7 | P2 | User Panel / Left Menu | Replace 'Shortlisted' with 'Inbox' (Incoming/Outgoing) for Legal/Tax/Accounting/Multimedia/Insurance | Done | Left menu: 'Shortlisted'->'Inbox' for all 5 consultancy categories; Incoming/Outgoing tabs retained; made nav ids unique per-category (fixes duplicate-id dropdown bug). Page heading + title -> Inbox.
8 | P2 | User Panel / Consultancy (Accounting) | Filters same as #5 (per-category service types) | Done | Accounting filters same as #5 with accounting-appropriate service types.
9 | P2 | User Panel / Consultancy (Tax) | Filters same as #5 (per-category service types) | Done | Tax filters same as #5 with tax-appropriate service types.
10 | P2 | User Panel / Consultancy (Multimedia) | Filters same as #5 (per-category service types) | Done | Multimedia filters same as #5 with multimedia-appropriate service types.
11 | P2 | User Panel / Consultancy (Insurance) | Filters same as #5 (per-category service types) | Done | Insurance filters same as #5 with insurance-appropriate service types.
12 | P1 | User Panel / Global styling | Form/filter/table labels 12px→15px, font-weight 600→500, consistent; darker grey for form/filter/table boxes | Done | Admin labels standardized to 15px/500 (.form-label, .admin-form-label, .consultancy-filter-label); darkened filter container bg (#E6EBF3) + box borders so boxes differentiate. Build passes.
13 | P3 | User Panel / Fake Profile | 'Advance - 100 per month' → 'Advance - 10 per month' | Done | ProfileFake: 'Advance - 100 per month' -> 'Advance - 10 per month'.
14 | P3 | User Panel / Buy-Sell | Add 'Verify Profile' to 3-dot (popup + Verification Code field + Verify btn); Date→Profile Name; remove Email; Amount→Asking Price | Done | Buy-Sell table: Date col -> Profile Name; removed email; Amount -> Asking Price. 3-dot menu adds 'Verify Profile' -> ProfileSellModal verify mode (Verification Code field + 'Verify' button).
15 | P3 | User Panel / Buy-Sell (Pending tab) | Field swaps; add Incoming Offer with 3-dot Accept/Decline/Counter Offer (confirmation boxes; counter has amount input); rename 'Pending'→'Incoming Offer' | Done | Pending tab renamed 'Incoming Offer'; field swaps applied; 3-dot for incoming offers = Accept/Decline/Counter Offer, each opens OfferActionModal confirmation (Counter has amount input).
15b | P3 | User Panel / Buy Profile | Revenue range→Asking Price range (dual-bar); new description; remove CA/Location/Experience; add Asking Price by name; Buy Profile popup Buy/Make Offer | Done | Buy Profile: Revenue Range -> Asking Price Range dual-bar (RangeSliderDropdown $10-$100K); summary -> CA description; removed CA/Location/Experience tags; Asking Price shown next to name; Buy Profile -> BuyProfileModal (Buy / Make Offer with amount input).
16 | P5 | User Panel / Dashboard | Sonam Kumari→John Doe; email/username updated; remove social links; move profile box to left | Done | Dashboard: Sonam Kumari->John Doe; email->johndoe@gmail.com; linktree->john_doe; removed social media links from profile card; profile box moved to LEFT (flex-row-reverse).
17 | P5 | User Panel / Dashboard | Social cards (john_doe); 2 charts (revenue vs paid-out + followers per platform); notifications box (incoming/outgoing collab offers); Recent Activity box w/ time filters | Done | Below profile: social-media cards (each shows john_doe + platform + followers); two charts (Revenue vs Paid Out, Followers by Platform); Collaboration Offers notifications box (incoming/outgoing badges + amount); Recent Activity box with time filter (24h/1w/1m/1y/5y/10y) + sort (date/amount/time).
18 | P4 | User Panel / Collaboration lists | Replace Post/Repost/Retweet with followers/following/posts; remove CA/Experience; Location→Country; platform descriptions; Activity analytics (avg last 10 posts); platform-specific Asking Rate — all platforms | Done | Collaboration lists: data restructured (country, followers/following/posts, activity avg-last-10, askingRate). Card now shows country + platform-labelled posts/followers/following; removed CA/Experience; Location->Country; platform-specific description; Activity analytics (likes/views/comments/reposts); platform-dependent Asking Rate. Platform derived from URL; per-platform labels (Tweets/Videos/Subscribers, Retweets/Shares etc.). All 6 platforms.
19 | P2 | User Panel / Consultancy Inbox (incoming) | Blue tags→service examples; add Avg Response Time 24h; add Hourly rate $500/hour — all services | Done | Inbox incoming: blue tags replaced with service-example tags (from category serviceTypes); added Avg Response Time: 24 Hours and Hourly rate: $500/hour. Applies to all categories via shared component.